## Sheet1
No. | Location | Item | Type | Priority | Date Identified | Date Resolved | Date Accepted | Status | Owner | Comments
1 | All dashboards | About caption update | Change | High | 2016-10-07 |  |  | Not started | Nick Karitsiotis | to drop in disclaimer on date range of data being analyzed
2 | All dashboards | Disclaimer | Change | Medium | 2016-10-07 |  |  | In progress | Nick Karitsiotis | disclaimer (similar to FDA) at top of each dashboard
3 | CV | search by generic | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | need to be able to search by generic name
4 | CV | About caption update | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | details on how searching for generic name
5 | All dashboards | Visualization by high level term | Change | Medium | 2016-10-07 |  |  | In progress | Nick Karitsiotis | not only preferred term
6 | All dashboards | About caption update | Change | Medium | 2016-10-07 |  |  | In progress | Nick Karitsiotis | disclaimer on the source of the data
7 | All dashboards | time series graphs to include total reports, serious reports and deaths | Change | High | 2016-10-07 |  |  | Not started | Nick Karitsiotis | currently just shows totals
8 | All dashboards | tool tip (mouse over event) | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | add to all titles, etc. to provide definitions, additional details
9 | All dashboards | expand clean up of drug tables | Defect | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis
10 | all dashboards | adding drug chart to identify concommitant and suspect | Change | low | 2016-10-07 |  |  | Not started | Nick Karitsiotis
11 | all dashboards | add histogram to calculate how many drugs per report | Change | low | 2016-10-07 |  |  | Not started | Nick Karitsiotis
12 | All dashboards | description of the age group breakdown on mouse over event | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis
13 | All dashboards | high level term graph | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis
14 | All dashboards | data export | Change | High | 2016-10-07 |  |  | In progress | Nick Karitsiotis | csv and excel format. Export all rows.
15 | FAERS | About caption update | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | disclaimer regarding integrity of FDA data
16 | FAERS | tool tip (mouse over event) | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | disclaimer that we are using FDA definitions that could change over time
17 | FAERS | About caption update | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | using american trade name and generic name definitions
18 | FAERS | fix age group error under patients tab | Defect | High | 2016-10-07 |  |  | Not started | Nick Karitsiotis
19 | FAERS | tool tip (mouse over event) | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | move chart captions into tool tip
20 | All dashboards | search terms | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | add handling for different combinations
21 | DISP | add checkbox for total graphs | Change | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis | total number of reports per quarter
22 | DISP | reporting RFET, RRR, gamma poissant shrink | Change | High | 2016-10-07 |  |  | Not started | Nick Karitsiotis | add these columns and calculations
23 | DISP | add sliders/checkboxes to control threshhold for what gets displayed in table | Change | High | 2016-10-07 |  |  | Not started | Nick Karitsiotis | count, exclude infinite, minimum expected count, top 100 drugs, vaccines
24 | DISP | fill in missing counts with zeros | Defect | Medium | 2016-10-07 |  |  | Not started | Nick Karitsiotis
25 | DISP | outcome validation | Change | High | 2016-10-14 |  |  | Not started | Dan Buijs | to begin at quality testing phase. Use matching datasets